## EstimationSheet
Test Case ID | Module/Feature | Test Case Description | Complexity (Low/Med/High) | Automation Feasibility (Yes/No) | Effort Estimate (hrs) | Script Owner | Planned Automation Date | Review Efforts | Remarks
Note on D1: Timir Trivedi: Low - Simple UI validations, no conditional logic, stable elements Medium - Involves conditional logic, minor waits, multiple screens High - Complex workflows, dynamic elements, multiple integrations (APIs, DB, Chart, PDF and Excel reading etc.)
Note on F1: Timir Trivedi: Complexity Estimation (hours) ---------- ------------------ Low 1–2 hours Medium 3–4 hours High 5–6+ hours

## Additional Factors
Categorize Test Case Complexity |  | Consider Additional Factors
Complexity | Description | Factor | Extra Effort
Low | Simple UI validations, no conditional logic, stable elements | New tool/framework adoption | +10–20% effort
Medium | Involves conditional logic, minor waits, multiple screens | Test data preparation | +0.5–1 hour per TC
High | Complex workflows, dynamic elements, multiple integrations (APIs, DB, Read Chart, PDF, Excel and Email etc.) | Environment setup/debugging | +1–2 hours (once-off)
|  | Code review & refactoring | +10–15% of total time
|  | Reporting & documentation | +5–10% of total time
Define Effort per Test Case (Estimation Benchmarks)
Complexity | Estimation (hours)
Low | 1–2 hours
Medium | 3–4 hours
High | 5–6+ hours