## 1440934
Marine Hull UK Dashboard Update – QA Estimation
Task | Description | Story Points | Est. Test Cases | QA Effort (hrs)
Changes to PPT slides | Apply new template, update slides, merge categories | 2 | 8 | 6
Changes to Excel format | Modify column headers, structure for utility input | 3 | 6 | 6
Update utility for new Excel input | Handle combined categories, new input format | 5 | 10 | 12
Update collections for new utility output | Adjust collections to reflect new processed data | 3 | 5 | 6
Update dashboard for new chart format | Modify chart logic for merged categories, UI changes | 5 | 12 | 10
Total |  | 18 | 41 | 40

## 1644878
Story Point Title | Description | Story Points | Est. Test Cases | QA Effort (hrs)
Summary Dashboard | Dashboard to select Risk Intake and initiate exposure capture | 3 | 5 | 4
Client Info | Pre-populate for renewal, search for new client, manual entry | 5 | 10 | 8
Logistics Questionnaire | Multi-section form (General Info, Ops Structure, Revenues, etc.) | 8 | 15 | 12
Non-Asset Operations | Form for Cargo Liability, Commodity Breakdown, etc. | 5 | 8 | 6
Carrier List | Carrier List table and supporting document uploads | 4 | 6 | 5
Warehouse | Warehouse liability, locations, contracts, and uploads | 6 | 10 | 8
Motor Cargo | Capture for motor cargo operations | 4 | 6 | 5
Shipper’s Interest | Capture shipper’s interest-related information | 4 | 6 | 5
Summary Page | Final review of captured information | 3 | 4 | 3
Thank You Screen | Confirmation screen, PDF download | 2 | 3 | 2
File Upload & PDF | Common functionality across steps for uploads and final PDF | 4 | 7 | 6
Total |  | 48 | 80 | 64

## Sheet1
Story Point Title | Workflow Step | Description | Story Points | Estimated Test Cases | QA Effort (hrs)
Broker Dashboard | 1. Broker Dashboard | Dashboard for brokers to view clients, placements, status, and create new applications | 3 SP | 6 | 5 hrs
Client Information | 2. Client Info (New/Renewal) | Capture client details, pre-population for renewal, manual entry for new clients | 5 SP | 10 | 8 hrs
Vessel Upload | 3. Upload Vessel Schedule | Template download and upload for vessel schedule in Excel format | 6 SP | 8 | 6 hrs
IMO Validation | 4. IMO Validation (Step 2 & 3) | Validate IMO numbers using algorithm, separate valid, invalid, and non-IMO vessels | 8 SP | 15 | 12 hrs
LLI API Lookup & Updates | 5. LLI Data Fetch & Error Tables | Fetch vessel details from LLI API, manage error tables, resolve duplicates | 7 SP | 12 | 10 hrs
Non-IMO Vessel Handling | 6. Non-IMO Vessel Handling | Handle vessels without IMO numbers (manual edits, adds, deletes) | 5 SP | 8 | 6 hrs
All Vessel Review | 7. Combined Vessel Review (Step 5) | Display master vessel list for final review before submission | 3 SP | 5 | 4 hrs
Compliance Screening | 8. Submit for Screening | Submit master schedule for compliance, show screening status | 4 SP | 6 | 5 hrs
Download Schedules | 9. Download Cleared Schedule | Download LLI-screened and Marsh-cleared schedules | 3 SP | 5 | 4 hrs
Thank You / Completion | 10. Completion & Exit Screen | Display confirmation and exit options | 2 SP | 3 | 2 hrs
Error Handling | 11. Error Handling (Invalid IMO) | Handle duplicates, invalid IMO entries, provide corrective actions | 4 SP | 7 | 6 hrs
Total | — |  | 50 SP | 85